## Sheet1
Used in Critical Path
| Activity | Start Date | Due Date | Precondition | Duration (Personal) |  | Duration (By Due Date)
A | Tutorial - Sigmoid Neurons | 2018-07-04 | 2018-07-11 |  | 4 |  | 7
B | Tutorial - Gradient Decent | 2018-07-11 | 2018-07-18 |  | 5 |  | 7
C | Tutorial - Backpropagation | 2018-07-18 | 2018-07-21 |  | 3 |  | 3
D | Tutorial - Segmentation | 2018-07-18 | 2018-07-21 |  | 3 |  | 3
E | Python - MNIST image setup | 2018-07-20 | 2018-07-23 |  | 1 |  | 3
F | Custom Training Data | 2018-07-23 | 2018-07-24 | A, B, C, D, E | 1 |  | 1
G | Unit Test Plan | 2018-07-18 | 2018-07-25 | F | 2 |  | 7
H | Testing - Personal Handwritting | 2018-07-25 | 2018-07-28 | F, G | 2 | MILSTONE II | 3
I | Output Format | 2018-07-28 | 2018-08-02 | H | 3 |  | 5
J | Basic UI | 2018-07-25 | 2018-08-08 | D | 6 |  | 14
K | Character Recognition | 2018-07-28 | 2018-08-11 | H | 7 |  | 14
L | Presentation | 2018-08-11 | 2018-08-15 | I, J, K | 2 |  | 4
Calculations
Early Start | No Precondition starts with 0 |  | With Single Precondition - Current Early Start = Precon Early Finish |  |  | With Multiple Preconditions - Current Early Start = Highest Precon Early Finish
Early Finish | Early Start + Duration
Late Start | Late Finish - Duration
Late FInish | No Forward starts with Early Finish |  | With Single Forward - Current Late Finish = Forward Late Start |  |  | With Multiple Forward - Current Late Finish = Lowest Forward Late Start
Critical Path | Nodes with same Early Finish and Late Finish